## Slide 1
SUMMARIZED STATUS OF ALL PROJECTS (PROJECT MANAGEMENT, IMPLEMENTATION & SUPPORT) |  |  |  |  |  | 
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
1 | Waveline | 1. Email Migration 2. Process Automation Next Steps Mobile Lending App | July, 2022 | May 2023 | 95% | 1. Email Migration Completed. 2. Process Automation completed 3. User Acceptance Testing Completed 4. JCD to be shared with Client for signoff
2 | EatonGate Capital | Mobile Lending App | July, 2022 | Dec. 2023 | 10% | Client put Project on hold to enable them do internal restructuring and recoup their funds from defaulting Customers. Completed Tasks: 1. Project Research 2. UI/UX Designs and Review 3. Frontend Development and Review
Legend | 0%-39%
 | 40%-69%
 | 70%-100%

## Slide 2
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
3 | KAM Holding | 1. Job Planning 2. Fleet Management 3. Assets Management 4. Facility Management 5. Office Space Management 6. Protocol and Corporate Services 7. Digitalization of Clinical operations 8. Marketing Application | Aug. 2022 | Jul. 2023 | 90% | Seven (7) Modules have been completed and deployed. Currently working on the Marketing Application which is proposed to be completed by June 2023.
4 | Digital Jewels Limited | PMO Automation: 1. Proposal Phase 2. Commencement Phase 3. Execution Phase 4. Completion Phase | Dec. 2022 | June, 2023 | 60% | Phase 1 and 2 of the PMO Project have been completed and approved by Client. Currently working on Phase 3 with the Client.

## Slide 3
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
5 | Muyideen Ola Nigeria Ltd | Automation of Business Processes | May 2023 | July 2023 | 35% | 1. POC deployed to Client's Environment. 2. Core Development of Full System has commenced and is proposed to be completed before end of July, 2023.
6 | Office of the Administrator (PAP) | Presidential Amnesty Program (PAP) Audit | May 2023 | Juy 2023 | 15% | 1. All documentations complete and executed 2. Vendor awaiting mobilization 3. Govt to disburse project initial funds
7 | EDC Facility Management Limited | Student/Admin Portal | May 2023 | July 2023 | 45% | 1. Project reviewed weekly with Vendor.

## Slide 4
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
8 | Lagos Angel Network (LAN) | Website Development and Maintenance | April 2023 | June, 2023 | 95% | 1. Website upgrade and revampe completed 2. Maintenance Services ongoing 3. JCD to be reviewed and share with Client
9 | Rising Tide Africa (RTA) | Website Revamp, Upgrade and Maintenance | May, 2023 | June, 2023 | 90% | 1. Website upgrade and revampe ongoing 2. Website optimization completed 3. Maintenance Services ongoing
10 | Angelika | Website Upgrade and Maintenance | May, 2023 | June, 2023 | 85% | Client to share product catalogue for upload to completed website upgrade. Maintenance Services ongoing
11 | Sabi Hub Limited | Website Upgrade and Maintenance | May, 2023 | June, 2023 | 85% | 1. Website has been restored 2. Maintenance Services ongoing
12 | GAIA Africa & Gaby Lagos | Websites Upgrade and Maintenance | May, 2023 | June, 2023 | 15% | Website Audit currently ongoing and when completed, we will commence the upgrade and update the plugins

## Slide 5
PROJECTS COMPLETED/CLOSED BETWEEN MARCH & JUNE 2023 |  |  |  |  |  | 
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
1 | Ekiti State Govt. | Land Use Charge (LUC) Deliverables: 1. Properties Enumeration 2. Automated Bill Generation 3. Bill Delivery to Residence 4. Collection of Payments | Oct. 2020 | Terminated | N/A | 1. Notice of Contract termination was issued by the Ekiti State Govt 2. Contracts of Temporal Staff terminated 3. Permanent Staff moved to Lagos Office