## Slide 1
Legend | 0%-39%
 | 40%-69%
 | 70%-100%
SUMMARIZED STATUS OF ALL PROJECTS (PROJECT MANAGEMENT/IMPLEMENTATION DEPT.) |  |  |  |  |  | 
sn | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
1 | Waveline | Proposed Solution(s): 1. Email Migration 2. Process Automation 3. Mobile Lending App Next Module: Mobile Lending App. | July, 2022 | May.2023 | 95% | 1. Email Migration Completed. 2. Process Automation completed 3. User Acceptance Testing (UAT) Completed 4. Job completion document shared with Client for signoff
2 | Junior Achievement Africa | Website Development for Management of Recruiters and Alumni | Feb. 23 | Jun. 2023 | 85% | 1. All modules except skills-testing completed. 2. User testing and bug fixing is on-going. 3. Job completion document to be shared with Client for signoff once item 2 above is completed.
3 | Four Point Hotel By Sheraton | Web and Mobile App Development for workspace Booking Management | Sept 2022 | Mar. 2023 | 90% | 1. Product has been built and deployed to client's environment. 2. Job completion document to be shared with Client for signoff.

## Slide 2
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
4 | KAM Holding | 1. Job Planning 2. Fleet Management 3. Assets Management 4. Facility Management 5. Office Space Management 6. Protocol and Corporate Services 7. Digitalization of Clinical operations 8. Marketing Application | Aug. 2022 | Jul. 2023 | 90% | Seven (7) Modules have been completed and deployed. Currently working on the Marketing Application which is proposed to be completed by June 2023.
5 | Digital Jewels Limited | PMO Automation: 1. Proposal Phase 2. Commencement Phase 3. Execution Phase 4. Completion Phase | Dec. 2022 | June, 2023 | 68% | Phase 1, 2 and 3 of the PMO Project have been completed and approved by Client. Currently working on Phase 4 with the Client.

## Slide 3
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
6 | Muyideen Ola Nigeria Ltd | Automation of Business Processes | May 2023 | July 2023 | 35% | 1. POC deployed to Client's Environment. 2. Core Development of Full System has commenced and is proposed to be completed before end of July, 2023.
7 | Office of the Administrator (PAP) | Presidential Amnesty Program (PAP) Audit | May 2023 | Juy 2023 | 15% | 1. All documentations complete and executed 2. Vendor awaiting mobilization 3. Govt to disburse project initial funds
8 | EDC Facility Management Limited | Student/Admin Portal | May 2023 | July 2023 | 45% | 1. Project to be reviewed weekly with Vendor.

## Slide 4
S/N | Client Name | Project(s) | Start Date | Est. End Date | Percentage Completion | Summary
9 | Lagos Angel Network (LAN) | Website Development and Maintenance | April 2023 | June, 2023 | 95% | 1. Website upgrade and revampe completed 2. Maintenance Services ongoing 3. JCD shared with Client for signoff
10 | Rising Tide Africa (RTA) | Website Revamp, Upgrade and Maintenance | May, 2023 | June, 2023 | 90% | 1. Website upgraded and revampe completed 2. Website optimization completed 3. Maintenance Services ongoing
11 | Angelika | Website Upgrade and Maintenance | May, 2023 | June, 2023 | 85% | 1. Website upgraded and revampe completed 2. Client to share product catalogue for upload to completed website upgrade.
12 | Sabi Hub Limited | Website Upgrade and Maintenance | May, 2023 | June, 2023 | 85% | 1. Website has been restored 2. Maintenance Services ongoing
13 | GAIA Africa & Gaby Lagos | Websites Upgrade and Maintenance | May, 2023 | June, 2023 | 15% | 1. Website Audit completed. 2. Audit Report shared. 3. Plugins ongoing.

## Slide 5
PROJECTS COMPLETED, ON HOLD OR CLOSED BETWEEN MARCH AND JUNE 2023 |  |  |  |  |  | 
sn | Client Name | Project(s) | Start Date | Estimated End Date | Percentage Completion | Summary
1 | Ekiti State Govt. | Land Use Charge (LUC) Deliverables: 1. Properties Enumeration 2. Automated Bill Generation 3. Bill Delivery to Residence 4. Collection of Payments | Oct. 2020 | Terminated | N/A | 1. Notice of Contract termination was issued by the Ekiti State Govt 2. Notice period has elapsed 3. Considerations for the Contract Staff (ongoing) 4. Relocation notice shared with Permanent Staff
2 | EatonGate Capital | Proposed Solution:Mobile Lending App | July, 2022 | On Hold | 10% | Client put Project on hold to enable them do internal restructuring and recoup their funds from defaulting Customers. Completed Tasks: 1. Project Research 2. UI/UX Designs and Review 3. Frontend Development and Review